(lll«fm<ffi

ncrtc•••••••••

••••••

<lwffi •

qRcrn-1f1lllf

J1«lil!}

National CapitalRegion Transport Corporation Limited

['- Joint v•nture of G0vemmen1 of lndi and pnrticlpming $!Dte-Govemmen1s)

# No.	NCRTC/CO-CEGoGEN/7/2024-GENERAL/379/2251

WORK EXPERIENCE CERTIFICATE (FOR COMPLETED WORKS}

Date:  01/01/2026

| 1. | Name of work | Designing, Fabrication, Installation and Management of NCRTC Exhibition at 'Tomorrow Mobility World Congress' organised at Fira Barcelona, Barcelona, Spain from 4th to 6th November 2025. |
| --- | --- | --- |
| 2 | Agreement no. | NIL |
| 3 | LOA No. & Date | NCRTC/CC/Conferences & Exhibitions/2025 dated 07.04.2022 |
| 4 | Name of Contractor & registered address | M/s LALIT ADVERTISING Ashoka Tower. C-Block, 10, Community Centre, Janakpuri, New Delhi-110058 |
| 5 | Constitution of the firm whether: proprietor, Partnership, LLP, Company, JV/ Consortium, Societv | Proprietorship Firm |
| 6 | PAN No. | AAGPJ4145F |
| 7 | If Joint Venture/consortium/ partnership firm, % share of each member · in JV/· consortium/ partnership | NA |
| 8 | Original awarded contract value | 17,47,500/- (Excluding. GST) |
| 9 | Revised/ Final contract value | 17,47,500/- (Excluding. GST) |
| 10 | Date of commencement of work | 04.11.2025 |
| 11 | Scheduled date of completion (As per contract) | 06.11.2025 |
| 12 | Actual date of completion | 06.11.2025 |
| 13 | If delay in execution on contractor's account | N.A. |
| 14 | Liquidated Damages levied for delay, if any | N.A. |
| 15 | Scope of work | The scope of work covers Designing, Fabrication, Installation and Management of NCRTC Exhibition at 'Tomorrow Mobility World Congress' organised at Fira Barcelona, Barcelona, Spain from 4th to 6th November 2025. |
| 16 | Overall performance of contractor | VeryGood |

# This certificate is issued on the request of M/s Lalit Advertising, for Business De elo

Office of ED / General

National capita\RegionTransportCorporationLid. (AJoinl VentureolGo\r1. otlrda &Pai'dcipating SlateGom.)

Ga\ishak1i Bha'llan,Ne1•1Dellll-lNA	Signed by Executive  Director/General

For and on behalf of NCRTC

Note: The above certificate has been uploaded on NCRTC website: - https://ncrtc.in/experience-certificate/

afcffi

: _-fujj_---i_cl_<f>_il_ _c:_ _ _<5_ _¥-=-, - -==(t'---X'>_3flcf

--.•ncrtc.in,  -

Registered & Corporate Office:

,,fcl ,f.ffi 1l<Fl.	110023

GatiShakti Bhawan, INA, New Delhi-110023

CIN: U60200DL2013GOl256716 Ph.: +91-11·2466670D

Fax: +91-11-24666723

E : contactus@ncrtc.in